## Start
SCMI – Migration plan
ConfigMgr → Microsoft Intune · worksheet for Module 15 – and for your project afterwards
Company / environment
Author
Date
Version | 0.1
How to use
Yellow cells | Your input. Everything else is a label, a formula or an example.
Grey rows | Example values from the SCMI lab pod – overwrite or delete them.
Dropdowns | Workload authority, routes, status and ratings are lists – pick, do not type.
Steps (35 min in the course)
1 Assessment | Counts that drive the effort – devices, apps / deployment types, GPOs, collections (M1).
2 Target state | Join type per device population, authority per workload, what stays in ConfigMgr (M2–M5, M12).
3 Waves | First three waves: scope, workloads, rollback owner, go and rollback criteria (M5, M13).
4 Risks | Top five risks with mitigation and owner – score is calculated.
5 Phases | Six phases with exit criteria and target dates – including the clean sweep (M13).
App tracking | Optional in the course: the factory tracking sheet from M10 for your project.
Summary (calculated)
Deployment types (assessment) | 0
Waves planned | 1
Risks with score ≥ 6 | 1
Phases with exit met | 0 of 6
Apps tracked | 1
Apps to retire | 0
Clean sweep target date | not set
Counts include the grey example rows until you delete them.

## 1 Assessment
1 · Assessment summary
Counts from your site and tenant. Lab column = SCMI pod values for comparison (M1).
Area | Metric | Where to get it | Your value | Lab (SCMI pod) | Notes
Devices | Devices with ConfigMgr client | Console → Devices, Client = Yes |  | 2
Devices | Hybrid joined | Entra → Devices, join type |  | 2
Devices | Entra joined | Entra → Devices, join type |  | 2
Devices | Domain joined only (not in Entra) | AD minus Entra – sync scope gaps |  | 0
Devices | Devices that cannot be cloud-managed | Air-gapped, regulated, special hardware |  | 0
Applications | Applications | Software Library → Applications |  | 10
Applications | Deployment types | Deployment Types tab – the unit of effort (M1) |  | 10
Applications | Applications without active deployment | Deployments column = 0 |  | 4
Applications | Packages / programs | Software Library → Packages |  | 1 / 2
Applications | Task sequences (non-OSD) | App chains, custom logic |  | 1
Policies | GPOs linked to workstation OUs | GPMC |  | 4
Policies | GPO settings without MDM support | Group Policy analytics (M6)
Policies | Configuration baselines / CIs | Assets and Compliance → Compliance Settings |  | 2 / 4
Policies | Custom client settings | Administration → Client Settings |  | 2
Targeting | Device collections | Assets and Compliance → Device Collections |  | 15
Targeting | Collections based on inventory | Queries joining SMS_G_System_* (M8) |  | 5
Targeting | Collections with maintenance windows | Collection properties |  | 1
Content | Distribution points / boundary groups | Administration → Distribution Points / Boundary Groups |  | 1 / 2
Content | Sites with thin lines | Network team |  | 1
Other | Custom reports, integrations on the site DB | SSRS, Power BI, scripts, CMDB feeds

## 2 Target state
2 · Target state
Who is managed how – and by whom – when the migration is done.
Device population | Devices | Join type today | Target join type | Path (M12) | Notes
Example: Sales laptops | 120 | Hybrid joined | Entra joined | Keep hybrid until refresh | Refresh cycle Q3, new devices via Autopilot
Workload authority
Workload | Today | Target | Planned in wave | Dependency / prerequisite | Notes
Compliance policies | ConfigMgr |  |  | Conditional Access design
Endpoint Protection | ConfigMgr |  |  | Defender onboarding, AV/firewall policies
Device configuration | ConfigMgr |  |  | GPO analysis, settings catalog profiles (M6)
Resource access | ConfigMgr |  |  | Moves with Device configuration
Windows Update policies | ConfigMgr |  |  | Rings, Autopatch decision (M11)
Office Click-to-Run apps | ConfigMgr |  |  | M365 Apps update channel
Client apps | ConfigMgr |  |  | App catalogue complete (M10)
Stays in ConfigMgr (scope, owner, end date)
Scope | Devices | Reason | Owner | End date / review | Notes
Example: Windows Server | 40 | Server patching | Server team | Review 2027 – Azure Arc

## 3 Waves
3 · Wave plan
One row per wave. Every wave needs a rollback owner and criteria agreed before it starts (M13).
Order of workloads in the course: Compliance → Endpoint Protection → Device configuration → Windows Update → Office C2R → Client apps. Microsoft allows any order.
Wave | Start | End | Scope (devices / users) | Devices | Workloads moved | Required apps ready | Staging collection | Entra group | Rollback owner | Go criteria | Rollback criteria | Status
0 | 2026-11-02 | 2026-11-13 | IT pilot – Vienna HQ | 15 | Compliance, Endpoint Protection | Yes | Pilot-CoMgmt | SCMI-DEV-Ring-Pilot | Workplace lead | No P1 tickets, compliance ≥ 95 % | > 3 P2 tickets / day or CA lockouts | Planned

## 4 Risks
4 · Top risks
Likelihood and impact 1 (low) – 3 (high). Score = likelihood × impact, ≥ 6 is highlighted.
ID | Risk | Category | Likelihood | Impact | Score | Mitigation | Owner | Course ref | Status
R0 | App catalogue not ready when Client apps should move | Applications | 3 | 2 | 6 | Factory with tracking sheet, retire first, PSADT template | App owner | M10 | Open
R1
R2
R3
R4
R5
Starting points from the course
Wave breaks productive devices → pilot rings, rollback levels (M13)
Conflicting configuration → one setting, one owner, GPO scoping (M7)
Identity problems block enrollment → hybrid join chain per wave (M2)
Co-management becomes permanent → clean sweep with end date (M13)
Late veto by security or works council → stakeholders in phase 0

## 5 Phases
5 · Phases and exit criteria
Phases 2–4 overlap in practice. The exit criterion makes progress measurable.
Phase | Content | Exit criterion | Your exit criterion | Owner | Target date | Status | Exit met
0 · Assess | Site, apps, policies, collections, identities (M1) | Assessment matrix complete
1 · Foundation | Hybrid join, tenant attach, co-management, enrollment (M2–M4) | Pilot devices co-managed
2 · Workloads | Waves per workload and ring (M5–M8, M11) | All workloads on Intune
3 · Applications | Factory: retire, Store / WinGet, Win32, PSADT (M9–M10) | Catalogue complete per ring
4 · Devices | New devices Entra joined, existing until refresh or reset (M12) | Hybrid share below target
5 · Clean sweep | Clients, records, GPOs, site (M13) | Site decommissioned or scoped
Checkpoint: the clean sweep (phase 5) has a target date.

## App tracking
App tracking – the factory (M10)
One row per ConfigMgr deployment type. Route decides the work; status shows progress.
ConfigMgr application | Deployment type | Owner | Route | Package / toolkit version | Detection | Test result | Intune app / assignment | ConfigMgr status | Wave | Notes
Mozilla Firefox ESR | Firefox ESR + policies | Workplace team | PSADT wrap | 1.0 / PSADT 4.1.x | MSI product code | Install, uninstall, prompt OK – CL4 | Win32, required: SCMI-DEV-Ring-Pilot | Deployment removed | 0